## Summary
MIRA Tech Debt Audit - 2026-04-25 - Summary
Total findings: 28 - Code: 7, Architecture: 20, Doc-Architecture: 1
By severity |  |  | By phase
Severity | Count |  | Phase | Count
Critical | 4 |  | Phase 1 - Sprint | 11
High | 9 |  | Phase 2 - 90-day MVP | 11
Medium | 14 |  | Phase 3 - Post-MVP | 6
Low | 1
By effort size
Effort | Count | Meaning
S | 11 | <= 1 day
M | 10 | 1-3 days
L | 5 | 1-2 weeks
XL | 2 | sprint+
Top 5 by score (foundation-first sequencing applied)
ID | Title | Severity | Score | Phase
DBT-010 | Tenant audit log allows UPDATE/DELETE under FOR ALL policy | Critical | 50 | Phase 1 - Sprint
DBT-002 | Three-layer LLM cascade with scattered failover | Critical | 40 | Phase 2 - 90-day MVP
DBT-009 | KEK rotation story missing from #574 | Critical | 40 | Phase 2 - 90-day MVP
DBT-007 | PII sanitizer not portable to mira-hub | High | 36 | Phase 2 - 90-day MVP
DBT-004 | 15+ scattered timeout literals | High | 35 | Phase 1 - Sprint

## Register
ID | Title | Module | File anchor | Category | Severity | Effort | Impact | Risk | Score | Phase | Why it matters | Concrete fix
DBT-001 | Supervisor god object | mira-bots | shared/engine.py (2531 LOC) | Architecture | Critical | L | 5 | 4 | 27 | 3 | engine.py mixes FSM, 5 workers, guardrails, fallbacks, work-order formatting, photo persistence in 2531 lines. Adding any feature touches this file. Merge conflicts compound across the parity sprint. | Extract FSMController, WorkerCoordinator, ResponseFormatter. Eval-gate each step. Schedule before file crosses 3000 lines.
DBT-002 | Three-layer LLM cascade with scattered failover | mira-bots, mira-pipeline | router.py:289; rag_worker.py:186; pipeline/main.py | Architecture | Critical | M | 5 | 5 | 40 | 2 | Router.complete() owns one cascade; RAG worker has its own 3-stage pipeline; pipeline wraps engine which calls RAG which calls router. A failover bug fixed in one layer doesn't reach the others. | Router owns cascade. RAGWorker calls router only. Pipeline calls engine only. Centralize telemetry at router level.
DBT-003 | Pipeline imports mira-bots via sys.path hack | mira-pipeline | mira-pipeline/main.py:32, 1107 | Architecture | High | M | 4 | 4 | 32 | 2 | sys.path.insert(0, ...) in two places. No declared dependency. Breaks packaging, deployment isolation, and type checking. | Package mira-bots/shared as publishable library. Declare in mira-pipeline/requirements.txt. Remove sys.path manipulation.
DBT-004 | 15+ scattered timeout literals | mira-bots, mira-pipeline | router.py 4x; engine.py 2x; nemotron.py; agents/*.py 5x; workers/*.py 3x | Code | High | S | 4 | 3 | 35 | 1 | Timeouts (15/30/60/120s) hardcoded in 15+ httpx.AsyncClient and asyncio.wait_for calls. Provider-degradation incident requires hunting and editing many files. | shared/config.py with TimeoutPolicy dataclass loaded at startup. All callers reference policy.
DBT-005 | _PROVIDER_HOURLY_LIMITS hardcoded in class dict | mira-bots | inference/router.py:218 | Architecture | High | S | 4 | 3 | 35 | 1 | Provider call budgets (groq:1800, cerebras:1800, gemini:900, claude:5000) baked into a class dict. Rate-limit incidents require code deploy. | Load INFERENCE_PROVIDER_LIMITS from Doppler env (JSON or comma-separated). Default to current values.
DBT-006 | Provider cascade order hardcoded | mira-bots | inference/router.py:_build_providers | Code | Medium | S | 3 | 3 | 30 | 1 | Provider order Groq -> Cerebras -> Gemini -> Claude is hardcoded. Comments explain historical reordering after Gemini 503s. Future reordering requires another deploy. | INFERENCE_PROVIDER_ORDER env var (comma-separated). Parse in _build_providers. Default to current order.
DBT-007 | PII sanitizer not portable to mira-hub | mira-bots, mira-hub | router.py:42-50 only | Architecture | High | M | 4 | 5 | 36 | 2 | Production IPv4/MAC/serial regex lives in mira-bots router.py. mira-hub asset-chat route has a 3-rule stub. PII can leak into chat responses on the new product surface. | Port regex to mira-hub/src/lib/pii-sanitizer.ts. Wrap as sanitizeContext(text). Call before LLM dispatch in /api/v1/assets/[id]/chat.
DBT-008 | libsodium wrapping duplicated | mira-hub | lib/llm-keys.ts + lib/webhooks/secret-storage.ts | Code | Medium | M | 3 | 4 | 28 | 2 | Both files independently implement getSodium loader, getKEK validation, nonce concatenation, stub mode. secret-storage.ts already has a TODO(#576) referencing this duplication. | Extract to mira-hub/src/lib/crypto/secretbox.ts: encryptSecretbox/decryptSecretbox. Both callers update.
DBT-009 | KEK rotation story missing from #574 | mira-hub | lib/llm-keys.ts (no key_id column) | Architecture | Critical | M | 5 | 5 | 40 | 2 | If LLM_KEK rotates, every encrypted llm_keys row becomes unreadable. No key_id, no re-encryption migration path. Doing this after launch is a customer-impacting outage. | Add key_id column referencing KEK version. Re-encryption migration path. Validate hex KEK at module load. Land before storing real customer keys.
DBT-010 | Tenant audit log allows UPDATE/DELETE under FOR ALL policy | mira-hub | db/migrations/2026-04-24-008-tenants-rls.sql | Architecture | Critical | S | 5 | 5 | 50 | 1 | FOR ALL policy on tenant_audit_log permits app-role UPDATE/DELETE. SOC 2 CC4.1 / CC7.2 require audit-log immutability. Blocks SOC 2 Type 1 evidence collection. | Split into FOR INSERT WITH CHECK (tenant_id_match) and FOR SELECT USING (tenant_id_match). No update/delete grant for app role.
DBT-011 | guardrails.py 986 LOC mixing 5 concerns | mira-bots | shared/guardrails.py (986 LOC) | Architecture | Medium | L | 3 | 3 | 18 | 3 | Single module owns SAFETY_KEYWORDS, classify_intent, check_output, resolve_option_selection, strip_mentions, vendor_name_from_text, vendor_support_url. Can't test vendor logic without safety logic. | Split into intent.py, safety.py, vendors.py, text_cleaning.py, option_resolution.py. Re-export from guardrails/__init__.py for compat.
DBT-012 | ingest main.py 1621 LOC | mira-core | mira-core/mira-ingest/main.py (1621 LOC) | Architecture | Medium | L | 3 | 3 | 18 | 3 | One 1.6k-line file handles photo ingest, visual search, document KB, Firecrawl, Apify, crawl verification, Reddit benchmark, Telegram notifications. Single point of change. | Refactor into routes/, pipelines/, services/. Example: routes/photo.py, services/scrape.py, services/verify.py. main.py keeps FastAPI setup only.
DBT-013 | pipeline main.py 1331 LOC (was ~500 on April 14) | mira-pipeline | mira-pipeline/main.py (1331 LOC) | Code | Medium | M | 3 | 3 | 24 | 2 | Pipeline grew 2.6x in 11 days. Mixes chat handlers, ingest helpers, regenerate-rollback logic, attachment download. Will keep absorbing scope if not split. | Split: chat handlers, ingest helpers, regenerate handler. Move OpenWebUI-specific regenerate logic to engine where FSM lives, not pipeline transport layer.
DBT-014 | MIME-type classification duplicated across 7 adapters | mira-bots | telegram/, slack/, teams/, gchat/, email/ chat_adapters | Code | Medium | S | 3 | 2 | 25 | 1 | Each adapter re-implements mime->kind mapping. _IMAGE_MIMES copied 4+ places. Adding a new mime requires 7 edits. | shared/chat/mime_utils.py with mime_to_kind(mime: str) -> Literal['image','pdf','other']. All adapters import.
DBT-015 | Image resize logic duplicated 3x with divergent MAX_VISION_PX | mira-bots, mira-pipeline | telegram/; whatsapp/bot.py:76; pipeline/main.py:75 | Code | Medium | S | 3 | 2 | 25 | 1 | _resize_for_vision implemented identically in 3+ places. MAX_VISION_PX = 1024 (pipeline) but 512 (whatsapp). Different image quality reaching vision models. | shared/image_utils.py with resize_for_vision(img, max_px). Single MAX_VISION_PX constant. All callers import.
DBT-016 | Two adapter abstractions coexist (MIRAAdapter + ChatAdapter Protocol) | mira-bots | shared/adapters/base.py vs ChatAdapter usages | Architecture | Medium | M | 3 | 2 | 20 | 3 | Email + WhatsApp extend MIRAAdapter base class. Telegram/Slack/Teams/GChat use ChatAdapter Protocol. Two parallel adapter patterns confuse maintainers. | Migrate Email + WhatsApp to ChatAdapter Protocol. Deprecate MIRAAdapter. Easier after dormant adapters (DBT-022) are archived.
DBT-017 | Duplicate cmms_write_work_order + cmms_create_work_order tools | mira-mcp | server.py:270 + 300 (both @mcp.tool) | Code | High | S | 4 | 3 | 35 | 1 | Both tools registered as MCP tools with identical signatures. cmms_create_work_order delegates to cmms_write_work_order with adapter fallback. Pollutes tool surface. | Retire cmms_write_work_order. Keep cmms_create_work_order with adapter fallback. Update REST routes.
DBT-018 | Tool surface bloat: 10 CMMS tools with overlapping intent | mira-mcp | server.py lines 154-595 (10+ @mcp.tool decorators) | Architecture | Medium | M | 3 | 3 | 24 | 2 | 10 CMMS tools (write/create/list/complete WO; list/get assets; list PMs; health; create-from-nameplate). Clients must understand fallback semantics. Prompts bloat. | Collapse into manage_cmms(action: str, params: dict). Returns union response. Reduces tool-search space ~5x.
DBT-019 | Schema drift between mcp SQLite and ingest NeonDB chunk shape | mira-mcp, mira-core | mcp/server.py:72-115 vs ingest/db/neon.py:345-404 | Architecture | High | L | 4 | 4 | 24 | 2 | mira-mcp stores equipment_photos with structured_description JSON. mira-core writes knowledge_entries with isa95_path/equipment_id/data_type. New field on one breaks recall on the other. | Define KnowledgeChunk dataclass in shared module. Both ingest and recall validate. Document mapping photos -> knowledge_entries.
DBT-020 | NeonDB migrations as ad-hoc ensure_* functions in app code | mira-core | mira-core/mira-ingest/db/neon.py:137-184 | Architecture | High | M | 4 | 4 | 32 | 2 | ensure_image_embedding_column, ensure_knowledge_hierarchy_columns called from FastAPI startup. Catch-all Exception. Failures leave DB inconsistent. No audit of what ran. | Move to db/migrations/ as numbered SQL files. Dedicated runner (Alembic or custom) at container startup. Log each migration outcome.
DBT-021 | mira-hub missing from CLAUDE.md repo map | repo-wide | CLAUDE.md (0 mentions of mira-hub) | Architecture | High | S | 4 | 3 | 35 | 1 | 14 in-flight feature branches per pre-merge-review. Module not in CLAUDE.md repo map. Onboarding agents have no signpost. Documentation drift. | Add mira-hub entry to CLAUDE.md repo map: 'Next.js 15 CMMS rebuild (Atlas migration target). 14 feature branches in parallel. Not yet in main.'
DBT-022 | Dormant adapter modules still building | mira-bots | mira-bots/{teams,whatsapp,reddit}/ | Architecture | Medium | S | 3 | 2 | 25 | 1 | Teams + WhatsApp dormant since March (per April 14 elegance audit). Reddit unclear if anyone uses. All still in compose, still build. | Move to attic/. Comment out of docker-compose. Remove from imports. Restore from git history if Azure/Twilio onboarding ever happens.
DBT-023 | Elegance-audit cleanups not executed (paperclip, mira_copy, bravo, ignition) | repo-wide | paperclip/, mira_copy/, bravo/, ignition/ | Architecture | Medium | S | 3 | 2 | 25 | 1 | April 14 elegance audit recommended archiving these. mira-hud and mira-prototype were actioned but these four were not. Dead weight in the repo. | git checkout -b archive/<dir>-2026-04 -- <dir>; git rm -r <dir>; commit. Document in CLAUDE.md Deferred / Archived table.
DBT-024 | Sidecar OEM migration: no owner, no ETA | mira-sidecar | tools/migrate_sidecar_oem_to_owui.py exists, never executed | Architecture | Medium | L | 3 | 3 | 18 | 2 | ADR-0008 plans sidecar sunset. 398 OEM chunks must move to Open WebUI KB first. Runbook exists. No tracking issue. No owner. No ETA. | File issue 'Archive mira-sidecar post-OEM migration'. Assign owner. Set 2026-06-01 target. Run runbook docs/runbooks/sidecar-oem-migration.md.
DBT-025 | known-issues.md stale on web cutover | docs | known-issues.md L17 vs mira-web/src/lib/mira-chat.ts:11 | Doc-Architecture | Low | S | 2 | 2 | 20 | 1 | known-issues.md says 'mira-web -> mira-pipeline cutover pending'. Verified: mira-chat.ts already calls pipeline:9099. Stale doc misleads agents. | Delete the bullet from known-issues.md. Add CHANGELOG.md entry: 'mira-web now calls mira-pipeline :9099 (ADR-0008).'
DBT-026 | 39 containers across compose overlays; 9 in mira-core | repo-wide | docker-compose*.yml | Architecture | Medium | XL | 3 | 3 | 6 | 3 | Per April 14 audit: 39 containers (4 compose topologies). 9 just in mira-core. Cognitive load + 39 healthchecks + 39 failure modes. | Two compose profiles: 'core' (target 12-15 containers) and 'full' (everything). Long-term elegance bet. XL scoped to multiple sprints.
DBT-027 | Atlas (mira-cmms) vs mira-hub strategy unclear | mira-cmms, mira-hub | both have asset/work-order schemas | Architecture | High | M | 4 | 4 | 32 | 2 | mira-cmms is Atlas (third-party Java/Postgres). mira-hub is parallel Next.js CMMS rebuild with own assets/work-orders/PMs. No ADR defines whether mira-hub replaces, integrates, or coexists. | Write ADR-0032: 'mira-hub CMMS strategy.' Decide replacement vs integration. Document data-migration path and Atlas sunsetting timeline if applicable.
DBT-028 | mira-crawler 11.9K LOC mixes KB ingest + GTM marketing | mira-crawler | mira-crawler/tasks/* (11+ task files) | Architecture | Medium | XL | 3 | 3 | 6 | 3 | Per April 14 audit: KB ingest tasks (discover, sitemaps, ingest, rss, gdrive) tangled with content-marketing tasks (blog, linkedin, social, content, youtube). Different products in same module. | Split into mira-crawler (KB ingest) and mira-content (GTM marketing). Separate Celery queues. Long-term.

## Phase 1 - Sprint
Phase 1 - Sprint (next 2 weeks): blast-radius reducers. 11/12 are S-effort. None block parity-sprint merges.
ID | Title | Severity | Effort | Score | One-line fix
DBT-010 | Tenant audit log allows UPDATE/DELETE under FOR ALL policy | Critical | S | 50 | Split into FOR INSERT WITH CHECK (tenant_id_match) and FOR SELECT USING (tenant_id_match). No update/delete grant for app role.
DBT-004 | 15+ scattered timeout literals | High | S | 35 | shared/config.py with TimeoutPolicy dataclass loaded at startup. All callers reference policy.
DBT-005 | _PROVIDER_HOURLY_LIMITS hardcoded in class dict | High | S | 35 | Load INFERENCE_PROVIDER_LIMITS from Doppler env (JSON or comma-separated). Default to current values.
DBT-017 | Duplicate cmms_write_work_order + cmms_create_work_order tools | High | S | 35 | Retire cmms_write_work_order. Keep cmms_create_work_order with adapter fallback. Update REST routes.
DBT-021 | mira-hub missing from CLAUDE.md repo map | High | S | 35 | Add mira-hub entry to CLAUDE.md repo map: 'Next.js 15 CMMS rebuild (Atlas migration target). 14 feature branches in parallel. Not yet in main.'
DBT-006 | Provider cascade order hardcoded | Medium | S | 30 | INFERENCE_PROVIDER_ORDER env var (comma-separated). Parse in _build_providers. Default to current order.
DBT-014 | MIME-type classification duplicated across 7 adapters | Medium | S | 25 | shared/chat/mime_utils.py with mime_to_kind(mime: str) -> Literal['image','pdf','other']. All adapters import.
DBT-015 | Image resize logic duplicated 3x with divergent MAX_VISION_PX | Medium | S | 25 | shared/image_utils.py with resize_for_vision(img, max_px). Single MAX_VISION_PX constant. All callers import.
DBT-022 | Dormant adapter modules still building | Medium | S | 25 | Move to attic/. Comment out of docker-compose. Remove from imports. Restore from git history if Azure/Twilio onboarding ever happens.
DBT-023 | Elegance-audit cleanups not executed (paperclip, mira_copy, bravo, ignition) | Medium | S | 25 | git checkout -b archive/<dir>-2026-04 -- <dir>; git rm -r <dir>; commit. Document in CLAUDE.md Deferred / Archived table.
DBT-025 | known-issues.md stale on web cutover | Low | S | 20 | Delete the bullet from known-issues.md. Add CHANGELOG.md entry: 'mira-web now calls mira-pipeline :9099 (ADR-0008).'

## Phase 2 - 90-day MVP
Phase 2 - 90-day MVP (through 2026-07-19): structural moves the parity-sprint merges and SOC 2 prep depend on.
ID | Title | Severity | Effort | Score | One-line fix
DBT-002 | Three-layer LLM cascade with scattered failover | Critical | M | 40 | Router owns cascade. RAGWorker calls router only. Pipeline calls engine only. Centralize telemetry at router level.
DBT-009 | KEK rotation story missing from #574 | Critical | M | 40 | Add key_id column referencing KEK version. Re-encryption migration path. Validate hex KEK at module load. Land before storing real customer keys.
DBT-007 | PII sanitizer not portable to mira-hub | High | M | 36 | Port regex to mira-hub/src/lib/pii-sanitizer.ts. Wrap as sanitizeContext(text). Call before LLM dispatch in /api/v1/assets/[id]/chat.
DBT-003 | Pipeline imports mira-bots via sys.path hack | High | M | 32 | Package mira-bots/shared as publishable library. Declare in mira-pipeline/requirements.txt. Remove sys.path manipulation.
DBT-020 | NeonDB migrations as ad-hoc ensure_* functions in app code | High | M | 32 | Move to db/migrations/ as numbered SQL files. Dedicated runner (Alembic or custom) at container startup. Log each migration outcome.
DBT-027 | Atlas (mira-cmms) vs mira-hub strategy unclear | High | M | 32 | Write ADR-0032: 'mira-hub CMMS strategy.' Decide replacement vs integration. Document data-migration path and Atlas sunsetting timeline if applicable.
DBT-008 | libsodium wrapping duplicated | Medium | M | 28 | Extract to mira-hub/src/lib/crypto/secretbox.ts: encryptSecretbox/decryptSecretbox. Both callers update.
DBT-013 | pipeline main.py 1331 LOC (was ~500 on April 14) | Medium | M | 24 | Split: chat handlers, ingest helpers, regenerate handler. Move OpenWebUI-specific regenerate logic to engine where FSM lives, not pipeline transport layer.
DBT-018 | Tool surface bloat: 10 CMMS tools with overlapping intent | Medium | M | 24 | Collapse into manage_cmms(action: str, params: dict). Returns union response. Reduces tool-search space ~5x.
DBT-019 | Schema drift between mcp SQLite and ingest NeonDB chunk shape | High | L | 24 | Define KnowledgeChunk dataclass in shared module. Both ingest and recall validate. Document mapping photos -> knowledge_entries.
DBT-024 | Sidecar OEM migration: no owner, no ETA | Medium | L | 18 | File issue 'Archive mira-sidecar post-OEM migration'. Assign owner. Set 2026-06-01 target. Run runbook docs/runbooks/sidecar-oem-migration.md.

## Phase 3 - Post-MVP
Phase 3 - Post-MVP (Q3+ 2026): big-ticket refactors. L/XL effort. Schedule before files cross next size threshold.
ID | Title | Severity | Effort | Score | One-line fix
DBT-001 | Supervisor god object | Critical | L | 27 | Extract FSMController, WorkerCoordinator, ResponseFormatter. Eval-gate each step. Schedule before file crosses 3000 lines.
DBT-016 | Two adapter abstractions coexist (MIRAAdapter + ChatAdapter Protocol) | Medium | M | 20 | Migrate Email + WhatsApp to ChatAdapter Protocol. Deprecate MIRAAdapter. Easier after dormant adapters (DBT-022) are archived.
DBT-011 | guardrails.py 986 LOC mixing 5 concerns | Medium | L | 18 | Split into intent.py, safety.py, vendors.py, text_cleaning.py, option_resolution.py. Re-export from guardrails/__init__.py for compat.
DBT-012 | ingest main.py 1621 LOC | Medium | L | 18 | Refactor into routes/, pipelines/, services/. Example: routes/photo.py, services/scrape.py, services/verify.py. main.py keeps FastAPI setup only.
DBT-026 | 39 containers across compose overlays; 9 in mira-core | Medium | XL | 6 | Two compose profiles: 'core' (target 12-15 containers) and 'full' (everything). Long-term elegance bet. XL scoped to multiple sprints.
DBT-028 | mira-crawler 11.9K LOC mixes KB ingest + GTM marketing | Medium | XL | 6 | Split into mira-crawler (KB ingest) and mira-content (GTM marketing). Separate Celery queues. Long-term.